## Summary
Metric | Value
Total_SQL_Files | 8
Total_Lines_of_Code | 1112
Average_Complexity_Score | 7.325
Total_Migration_Hours | 120
High_Risk_Components | 2
Medium_Risk_Components | 3
Low_Risk_Components | 3
Estimated_Cost_USD | 18000
Recommended_Timeline_Weeks | 1

## Complexity_Analysis
File_Name | Lines_of_Code | Complexity_Score | Functions_Used | Table_References | Migration_Hours | Risk_Level | Category | SQL_Features | Source_Database | Target_Platform | Assessment_Date
supply_chain_performance.sql | 145 | 8.5 | 12 | 8 | 16 | Medium | Analytics | CTEs, Window Functions, Complex Joins | GlobalSupply_DW | Databricks | 2025-09-18
inventory_optimization.sql | 198 | 9.2 | 18 | 6 | 24 | High | Analytics | Recursive CTEs, PIVOT, Advanced Analytics | GlobalSupply_DW | Databricks | 2025-09-18
customer_profitability.sql | 167 | 7.8 | 14 | 7 | 18 | Medium | Analytics | PIVOT, Window Functions, String Aggregation | GlobalSupply_DW | Databricks | 2025-09-18
supplier_risk_assessment.sql | 223 | 9.8 | 22 | 9 | 32 | High | Analytics | Recursive CTEs, Dynamic SQL, Risk Scoring | GlobalSupply_DW | Databricks | 2025-09-18
dynamic_reporting.sql | 89 | 6.5 | 8 | 5 | 8 | Low | Reporting | Dynamic SQL, Conditional Logic | GlobalSupply_DW | Databricks | 2025-09-18
window_functions_analysis.sql | 134 | 7.2 | 16 | 4 | 12 | Medium | Analytics | Advanced Window Functions, LAG/LEAD | GlobalSupply_DW | Databricks | 2025-09-18
financial_summary.sql | 67 | 4.5 | 6 | 3 | 4 | Low | Reporting | Basic Aggregation, Simple Joins | GlobalSupply_DW | Databricks | 2025-09-18
order_processing.sql | 89 | 5.1 | 9 | 4 | 6 | Low | OLTP | CRUD Operations, Transactions | GlobalSupply_DW | Databricks | 2025-09-18

## Dependencies
Source_Object | Target_Object | Dependency_Type | Criticality | Impact_Score
customer_profitability.sql | financial_summary.sql | View | High | 8
supplier_risk_assessment.sql | supply_chain_performance.sql | Procedure | High | 9
inventory_optimization.sql | order_processing.sql | Table | Medium | 6
supply_chain_performance.sql | dynamic_reporting.sql | View | Medium | 7
window_functions_analysis.sql | customer_profitability.sql | Function | Low | 4
order_processing.sql | financial_summary.sql | Table | Medium | 5

## Function_Usage
Function_Name | Usage_Count | Complexity_Impact | Databricks_Compatibility | Migration_Effort
ROW_NUMBER | 15 | 3 | Direct | 0
RANK | 12 | 3 | Direct | 0
LAG | 8 | 4 | Direct | 0
LEAD | 6 | 4 | Direct | 0
SUM | 25 | 1 | Direct | 0
AVG | 20 | 1 | Direct | 0
COUNT | 30 | 1 | Direct | 0
DATEDIFF | 18 | 2 | Modified | 2
DATEADD | 14 | 2 | Modified | 2
STRING_AGG | 5 | 4 | Modified | 4
PIVOT | 3 | 5 | Modified | 6
CASE | 22 | 2 | Direct | 0
CTE | 18 | 3 | Direct | 0
RECURSIVE_CTE | 2 | 5 | Complex | 8
STDEV | 4 | 3 | Direct | 0
VAR | 3 | 3 | Direct | 0

## Migration_Waves
File_Name | Lines_of_Code | Complexity_Score | Functions_Used | Table_References | Migration_Hours | Risk_Level | Category | SQL_Features | Source_Database | Target_Platform | Assessment_Date | Migration_Wave
supply_chain_performance.sql | 145 | 8.5 | 12 | 8 | 16 | Medium | Analytics | CTEs, Window Functions, Complex Joins | GlobalSupply_DW | Databricks | 2025-09-18 | Wave 2 - Standard Migration
inventory_optimization.sql | 198 | 9.2 | 18 | 6 | 24 | High | Analytics | Recursive CTEs, PIVOT, Advanced Analytics | GlobalSupply_DW | Databricks | 2025-09-18 | Wave 3 - Complex Components
customer_profitability.sql | 167 | 7.8 | 14 | 7 | 18 | Medium | Analytics | PIVOT, Window Functions, String Aggregation | GlobalSupply_DW | Databricks | 2025-09-18 | Wave 2 - Standard Migration
supplier_risk_assessment.sql | 223 | 9.8 | 22 | 9 | 32 | High | Analytics | Recursive CTEs, Dynamic SQL, Risk Scoring | GlobalSupply_DW | Databricks | 2025-09-18 | Wave 3 - Complex Components
dynamic_reporting.sql | 89 | 6.5 | 8 | 5 | 8 | Low | Reporting | Dynamic SQL, Conditional Logic | GlobalSupply_DW | Databricks | 2025-09-18 | Wave 2 - Standard Migration
window_functions_analysis.sql | 134 | 7.2 | 16 | 4 | 12 | Medium | Analytics | Advanced Window Functions, LAG/LEAD | GlobalSupply_DW | Databricks | 2025-09-18 | Wave 2 - Standard Migration
financial_summary.sql | 67 | 4.5 | 6 | 3 | 4 | Low | Reporting | Basic Aggregation, Simple Joins | GlobalSupply_DW | Databricks | 2025-09-18 | Wave 1 - Quick Wins
order_processing.sql | 89 | 5.1 | 9 | 4 | 6 | Low | OLTP | CRUD Operations, Transactions | GlobalSupply_DW | Databricks | 2025-09-18 | Wave 1 - Quick Wins